## Demo data
Project ID | Project No | Project Name | Province | Department | Local Municipality | District Municipality | Latitude | Longitude | Project Status | Project Start Date | Estimated Construction Start Date | Estimated Project Completion Date | Contracted Construction End Date | Estimated Construction End Date | Professional Fees | Construction Costs | Variation Orders | Total Project Cost | Project Projected Expenditure from Previous Financial Years (Professional Fees) | Project Expenditure from Previous Financial Years (Professional Fees) | Project Expenditure from Previous Financial Years (Construction Costs) | Project Expenditure from Previous Financial Years (TOTAL) | Project Expenditure (TOTAL) | Main Budget Appropriation (Professional Fees) | Adjustment Budget Appropriation (Professional Fees) | Main Budget Appropriation (Construction Costs) | Adjustment Budget Appropriation (Construction Costs) | Main Budget Appropriation (TOTAL) | Adjustment Budget Appropriation (TOTAL) | Actual Expenditure Q1 | Actual Expenditure Q2 | Actual Expenditure Q3 | Actual Expenditure Q4 | Budget Programme | Primary Funding Source | Nature of Investment | Funding Status | No. jobs created | No. youth employed | No. women employed | No. people with disabilities employed | No. FTEs | No. people trained | Person days worked | Average employment period | Minimum wage | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor | Project Contractor
30682 | W/50042423/WS | BLUE JUNIOR SECONDARY SCHOOL | KwaZulu-Natal | Education | Dr Nkosazana Dlamini Zuma | Harry Gwala | -30.0303 | 29.6035 | Design | 2016-06-13 | 2017-02-01 | 2021-06-30 |  |  | 118000 | 562000 | 0 | 680000 | 446279 | 556479 |  | 556479 | 1315479 | 61000 | 0 | 276000 | 0 | 337000 | 0 |  |  |  |  | Programme 2 - Public Ordinary School Education | Education Infrastructure Grant | Upgrading and Additions | Tabled | [9 empty] | Program Implementing Agent: DOPW
29210 | W/500247937/W | PINK PRIMARY SCHOOL | KwaZulu-Natal | Education | Richmond | Umgungundlovu | -29.9615 | 30.2131 | Tender | 2016-06-23 | 2017-06-23 | 2020-04-30 |  |  | 750000 | 1500000 | 0 | 2250000 | 314305 | 451096 |  | 451096 | 2505096 | 307000 | 0 | 1397000 | 0 | 1704000 | 0 |  |  |  |  | Programme 2 - Public Ordinary School Education | Education Infrastructure Grant | Upgrading and Additions | Tabled | [9 empty] | Program Implementing Agent: DOPW |  |  | Program Implementing Agent: Transport and Public Works
28123 | W/50042742/SDS | GREEN PRIMARY SCHOOL | KwaZulu-Natal | Education | eThekwini | eThekwini | -30.0057 | 30.9265 | Feasibility | 2016-06-14 | 2016-07-29 | 2021-06-30 |  |  | 48649 | 221621 | 0 | 270270 | 175658 | 242448 | 77610 | 320058 | 1373058 |  |  | 2000 | 0 | 2000 | 0 |  |  |  |  | Programme 2 - Public Ordinary School Education | Education Infrastructure Grant | Upgrading and Additions | Tabled | [9 empty] | Program Implementing Agent: DOPW
28128 | W/50011026/SDS | YELLOW PARK PRIMARY SCHOOL | KwaZulu-Natal | Education | The Msunduzi | Umgungundlovu | -29.6489 | 30.3936 | Practical Completion (100%) | 2016-06-13 | 2017-07-01 | 2017-11-30 | 2018-09-01 | 2020-04-01 | 48649 | 221621 | 0 | 270270 | 200360 | 391267 | 1315291 | 1706558 | 2761558 | 64000 | 0 | 242000 | 0 | 306000 | 0 |  |  |  |  | Programme 2 - Public Ordinary School Education | Education Infrastructure Grant | Maintenance and Repairs | Tabled | [9 empty] | Program Implementing Agent: DOPW
28120 | W/50103008/WS | RED SECONDARY SCHOOL | KwaZulu-Natal | Education | Okhahlamba | Uthukela | -28.6811 | 29.0464 | Construction 76% - 99% | 2016-02-20 | 2016-08-19 | 2018-03-30 | 2018-09-01 | 2021-05-31 | 434000 | 1979000 | 0 | 2413000 | 326579 | 354779 | 1604459 | 1959238 | 2159238 | 200000 | 0 |  |  | 200000 | 0 | 20075 | 0 | 0 | 0 | Programme 2 - Public Ordinary School Education | Education Infrastructure Grant | Upgrading and Additions | Tabled | [9 empty] | Program Implementing Agent: DOPW
12217 | CDC/47308 | Swing Swimming Pool | Eastern Cape | Sports, Recreation, Arts and Culture | Mnquma | Amathole | -32.3323 | 28.1446 | Construction 76% - 99% | 2016-10-27 | 2016-11-01 | 2018-06-30 | 2017-05-31 | 2022-03-31 | 2038000 | 18342000 | 0 | 20380000 | 2287122 | 2287122 | 15447375 | 17734497 | 20438497 |  |  | 2500000 | 0 | 2500000 | 0 | 0 | 474455 | 0 | 0 | Programme 4 - Sports and Recreation | Equitable Share | New or Replaced Infrastructure | Tabled | [9 empty] | Program Implementing Agent: CDC
12223 | AR2455 | Tree Library | Eastern Cape | Sports, Recreation, Arts and Culture | Mhlontlo | O.R.Tambo | -31.1596 | 28.8946 | Tender | 2015-04-01 | 2016-07-18 | 2023-03-31 |  |  | 0 | 25500000 | 0 | 25500000 |  | 179968 | 297839 | 477807 | 12998807 |  |  | 275000 | 0 | 275000 | 0 |  |  |  |  | Programme 3 - Library and Archives Services | Community Library Service Grant | New or Replaced Infrastructure | Tabled | [9 empty] | Principal Agent: |  |  | Principal Agent: Nelson Barabosa Architects
12232 |  | Modded Modular Library | Eastern Cape | Sports, Recreation, Arts and Culture | Engcobo | Chris Hani | -31.6728 | 27.9835 | Pre - Feasibility | 2015-04-01 | 2015-04-25 | 2020-03-31 | 2020-03-02 | 2020-03-31 | 0 | 1094000 | 0 | 1094000 |  |  | 1093510 | 1093510 | 1443510 |  |  | 350000 | 0 | 350000 | 0 |  |  |  |  | Programme 3 - Library and Archives Services | Community Library Service Grant | Upgrading and Additions | Tabled | [9 empty] | Principal Agent: Fabricated Steel Manufacturing
14337 | 100328 | Dreizehn Laerskool | North West | Education & Training | City of Matlosana | Dr Kenneth Kaunda | -26.8472 | 26.7679 | Practical Completion (100%) | 2015-02-11 | 2015-02-13 | 2016-02-15 | 2016-02-29 | 2016-03-01 | 0 | 5661000 | 0 | 5661000 |  |  | 4161366 | 4161366 | 4311366 |  |  | 150000 | 0 | 150000 | 0 |  |  |  |  | Programme 6 - Infrastructure Development | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment | Tabled | 96 | 81 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | Program Implementing Agent: Department of Public Works
12255 | FBL | Book Worm Library | Eastern Cape | Sports, Recreation, Arts and Culture | Raymond Mhlaba | Amathole | -32.7663 | 26.62 | Design | 2016-04-01 | 2016-11-23 | 2022-03-31 |  |  | 792000 | 5808000 | 0 | 6600000 | 0 | 0 | 144556 | 144556 | 5685556 |  |  | 3500000 | 0 | 3500000 | 0 |  |  |  |  | Programme 3 - Library and Archives Services | Community Library Service Grant | Rehabilitation, Renovations & Refurbishment | Tabled | [9 empty] | Principal Agent:
14318 | 100303 (2) | Testy test Secondary | North West | Education & Training | City of Matlosana | Dr Kenneth Kaunda | -26.8466 | 26.8657 | Project Initiation | 2016-03-01 | 2016-04-01 | 2019-08-01 |  |  | 0 | 3733000 | 0 | 3733000 |  |  | 702280 | 702280 | 726280 |  |  | 24000 | 0 | 24000 | 0 |  |  |  |  | Programme 6 - Infrastructure Development | Education Infrastructure Grant | Rehabilitation, Renovations & Refurbishment | Tabled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Program Implementing Agent: Department of Public Works